## Slide 2
2
3
PROJECT SCHEDULE
1
DESIGN PHASES
SCHEMATIC DESIGN

## Slide 3: 1 PROJECT SCHEDULE

## Slide 4
  PROJECT SCHEDULE – DESIGN PHASE
  July – September 2020 Programming / Preliminary Design
  October – November 2020 Schematic Design – “Exploration”
  December – February 2021 Design Development – “Refinement”
  Act 34 Public Hearing
  March – April 2021 Construction Documents – “Preparation”
  Note:
  Board Action required at end of each Design Phase
  Schedule is pending Municipal and Regulatory Agency Approvals
  Estimated Start of Construction in July 2021

## Slide 5
  BOARD UPDATES & APPROVALS
December 3, 2020 Board Approval: Schematic Design
January 11, 2021 Board Review of Building DD Phase
February 8, 2021 Board Review of Building DD Phase
March 8, 2021 Board Approval: Design Development & Act 34 Booklet
April 12, 2021 Board Approval: Release Project for Bidding
May/June 2021 Tentative Bid Receipt
June 2021 Board Approval: Intent to Award
July 2021 Issue Notice to Proceed: Start Construction

## Slide 6
  ACT 34 PUBLIC HEARING SCHEDULE
  Step #1 Board Approval of Maximum Building Construction Cost / Review Draft Act 34 Booklet
  Step #2 Architect submits Act 34 Booklet to PA Department of Education for review and approval to advertise
  Step #3 School District and Solicitor coordinate advertisement 20 days prior to Hearing date
  Step #4 Act 34 Public Hearing, conducted by School District, Solicitor, Architect and Financial Consultant
  Step #5 End of 30 day waiting period to compile proof of publication, written comments and Hearing minutes

## Slide 7: 2 DESIGN PHASES

## Slide 8
  NOTE: The images in the upcoming slides do not represent the design of the Chicora Elementary School additions and renovations. These example images are used to illustrate project development and detail throughout the various design phases.

## Slide 9
  Schematic Design Phase
  1. Programming:
  Document Educational Program.
  2. Site Analysis:
  Establish Project Goals and Site Considerations, Site Survey of Existing Conditions, determine necessary approvals.
  3. Conceptual Plans:
  Establish Building Organization, Prioritize Program and Site Adjacencies and Develop Traffic Circulation.
  4. Schematic Plans:
  Develop Floor Plans based on Educational Program and existing site conditions
  PROJECT EXAMPLES

## Slide 10
  Design Development Phase
  1. Civil Engineering:
  Site design of vehicular circulation, parking, drop-off areas, pedestrian connections. Land Development submission with storm water management plans.
  2. Architectural Plans:
  Refinement of Floor Plans, final check of Educational Program, meetings with Faculty to develop Interior layouts, establish Floor Plans to begin design of structural, food service, mechanical, electrical and plumbing systems.
  PROJECT EXAMPLES

## Slide 11
  Construction Documents Phase
  1. Civil Engineering:
  Acquire necessary permits and approvals required for construction.
  2. Architectural Plans:
  Final production of Construction Documents with coordination and integration of building systems including structural, food service, mechanical, plumbing, electrical and civil engineering.
  PROJECT EXAMPLES

## Slide 12: 3 SCHEMATIC DESIGN

## Slide 13
  Schematic Site Plan
  Existing Building
  New Addition
Bus Drop-Off
Parent Drop-Off
Dock
Play Area
Softball/Practice Field
Overflow Parking
Visitor Parking
Staff Parking
Spring Street Access Drive

## Slide 14
  Educational Program
  Planned Student Capacity
  Quantity and Size of Educational Spaces
  Outline of Support Spaces
  Needed Adjacencies of Spaces

## Slide 15
  Schematic Floor Plan
  General Classrooms
  Special Education
  Small Group Instruction
  Music
  Art
  Library/Cafeteria/Gymnasium
  Faculty
  Building Support
KEY PLAN

## Slide 16
QUESTIONS?